## Sheet1
|  | Tri 1 | [16 empty] | Tri 2
Task |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
IPO | bar: Tri 1 1 to Tri 1 3
Research | Library Search | bar: Tri 1 3 to Tri 1 4
Current Products | bar: Tri 1 4 to Tri 1 5
Writing | Abstract
Intro
Lit Review | bar: Tri 1 3 to Tri 1 7
Method
Results
Evaluation
Conclusion
Appendicies + Bib
Coding | Store Image
Process Image
Compare Processed Images
Calculate Pressure
App
Assessment | Week 9 Review | bar: Tri 1 9 to Tri 1 11
Viva Voce | bar: Tri 2 12
Poster Club | bar: Tri 2 12